## Instructions
Use this spreadsheet to prepare Project Progress Dashboards, similar to the sample below.
This is a model, you will need to adapt it to your needs, but it's a good starting point J.
Read the instructions in the yellow boxes on each sheet.
Happy dashboarding,
Maurice Calvert

## All4
Projects' Status Summary
Don't modify this sheet, it's build from the other tabs with corresponding names.
To insert this in Powerpoint:
Select the named range "Overview", copy and paste into Powerpoint as a Windows enhanced meta file and scale to 85%

## GlobalStatus
Global | Global | Risks | Timing | Budget | HR | Infra
Project 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project 2 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project 4 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project 5 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project 6 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
0
0
Don't modify this sheet, it's built from the Consolidated tab

## Finance
Finance | Budget | Spent | Projected | Total | Total / Budget
Project 1 | 35000 | 11000 | 26000 | 37000 | 105.7%
Project 2 | 70000 | 34500 | 31000 | 65500 | 93.57%
Project 3 | 8000 | 2300 | 5400 | 7700 | 96.25%
Project 4 | 14000 | 9700 | 3900 | 13600 | 97.14%
Project 5 | 24000 | 13800 | 9700 | 23500 | 97.92%
Project 6 | 28000 | 19300 | 11000 | 30300 | 108.2%
Don't modify this sheet, it's built from the Consolidated tab

## Highlights
Highlights
Project1 | Draft specifications complete
Project2 | Routers delivered
Firewall intrusion test OK
Network ready
Project 3 | Business plan accepted
Fill-in columns B and C.
Don't change formatting

## Risks
Risks
Project1 | #VALUE! | Business specifications not ready | 1 | 1=Green, 2=Yellow, 3=Red
| #VALUE! | Budget not approved | 2
Project 2 | #VALUE! | Intrusion test failure | 3
1
2
3
Modify columns B, C and D.
The traffic light appears when there is text in D. To remove surplus lights, use the Remove Lights button

## Consolidated
| Global | [11 empty] | Finance
| Global |  | Risks |  | Timing |  | Budget |  | HR |  | Infra |  | Budget | Spent | Projected | Total | Total / Budget
Thresholds | 35 | 75 | 35 | 75 | 35 | 75 | 35 | 75 | 35 | 75 | 35 | 75
Project 1 |  |  | 80.7914 |  | 20.4106 |  | 23.5376 |  | 29.6621 |  | 92.5848 |  | 35000 | 11000 | 26000 | 37000 | 105.7%
Project 2 | 76.5253 |  | 73.377 |  | 44.287 |  | 31.3619 |  | 42.761 |  | 83.4411 |  | 70000 | 34500 | 31000 | 65500 | 93.57%
Project 3 | 86.744 |  |  |  | 24.3011 |  | 65.9571 |  | 93.956 |  | 99.6446 |  | 8000 | 2300 | 5400 | 7700 | 96.25%
Project 4 | 3.0555 |  | 95.3328 |  | 40.2494 |  | 51.0534 |  | 92.1045 |  | 63.5257 |  | 14000 | 9700 | 3900 | 13600 | 97.14%
Project 5 | 94.9407 |  | 47.6281 |  | 84.2576 |  | 85.2841 |  | 60.9013 |  | 89.0931 |  | 24000 | 13800 | 9700 | 23500 | 97.92%
Project 6 | 59.9145 |  | 43.9071 |  | 75.7666 |  | 4.2185 |  | 71.4284 |  | 16.4372 |  | 28000 | 19300 | 11000 | 30300 | 108.2%
Fill in the light blue cells
The thresholds set the colour of the traffic light, red below 35, yellow from 35 to 75, green above

## Setup
Light size | 20 | diameter of traffic lights in pixels
Set B3 to the desired diameter of your traffic lights

## Project1Display
#VALUE! | Project 1 Status |  | Budget 35'000 Spent 11'000 Total 37'000
Highlights |  | Manpower | Budget 220 Spent 180 Total 245
Complete
Activity 1
Activity 2
Activity 3
Planned
Activity 1
Activity 2
Activity 3
Contracts
Contract details 1
Contract details 2
Contract details 3
Don't modify this sheet.
Duplicate it and Project1Burn for each project. You'll need to change the formulas in H2 and H5 to point to the correct numbers in the Consolidated tab.
For Powerpoint, select the named range "Project1", copy and paste as a windows metafile

## Project1Burn
Project budget | 220 | man/days
Projected total | 245
Project start | 2008-08-01
Project end | 2009-02-28
Working days | #VALUE!
Monthly burn | #VALUE!
Date | Month | Effort
2008-08-31 | 2008-08-31 | 42
2008-09-30 | 2008-09-30 | 38
2008-10-31 | 2008-10-31 | 56
2008-11-30 | 2008-11-30 | 44
180
Formulas:
Month = [Date]
These numbers create the Manpower barchart in the ProjectDisplay tab
In ProjectDisplay tab:
- Fill out activities and Contracts
- Update figures in ProjectBurn
- Paste your Gant bottom right
- Select named range "Project1"
- Copy and Paste special Windows Metafile in Powerpoint. Font colours may get trashed - this is a bug in the handling of colour palettes in Windows L